## Sheet1
DETECTION OF HEART DISEASE FROM SPECT DATA
USING SUPPORT VECTOR MACHINES

TASKS	PLANNED		DURATION	DAYS	DAYS	%	WK1	WK2	WK3	WK4	WK5	WK6	WK7	WK8	WK9	WK10	WK11	WK12	WK13	WK14	WK15	WK16	WK17	WK18	WK19	WK20	WK21
	START	END	(DAYS)	COMPLETE	REMAINING	COMPLETED
	DATE	DATE

1. Problem definition	01/10/12	15/01/12	6	6	0	100.00%

2. Find research papers	16/01/12	22/01/12	7	7	0	100.00%

3. Define scope	23/01/12	25/01/12	3	3	0	100.00%

4. Initial specifications	30/01/12	02/10/12	11	11	0	100.00%

5. Find SPECT data	02/11/12	31/03/12	51	51	0	100.00%

6. Design specification	16/02/12	27/02/12	12	12	0	100.00%

7. Prototype impl.	03/01/12	31/03/12	31	31	0	100.00%

8. Impl. refinement	04/01/12	25/04/12	26	26	0	100.00%

9. Debugging & Testing	26/04/12	05/10/12	15	15	0	100.00%

10. Documentation	05/11/12	20/05/12	10	10	0	100.00%